## Slide 1: CEN/WS XBRL
12 December, 2012
Overview

## Slide 2: CEN Workshop
The CEN Workshop is a flexible working platform open to the participation of any company or organisation, inside or outside Europe, for rapid elaboration of consensus documents (CWAs).

## Slide 3: STATUS EUROPESE STANDAARDEN

## Slide 4: CEN/WS XBRL Summarized
Workshop duration is 23 months
3 deliverables
Public consulatation period
Financial support from the EC (expert teams)

## Slide 5: CEN/WS XBRL deliverables
CWA 1 Standardize harmonization topics
CWA 2 Metadata container and compliance tools
CWA 3 Standard regulatory roll-out package for better adoption

## Slide 6: CEN WS XBRL Structure
Chair
Ignacio Boixo
Chairman Advisory Group (CAG)
Secretariat
Maarten Peelen
CEN WS XBRL Decision-making body
Project Team D Coordination across deliverables
Working Group 1 CWA 1: Harmonization topics
Katrin Heinze
Project Team A
Working Group 2 CWA 2: Metadata container
Emile Bartolé
Project Team B
Working Group 3 CWA3: Standardized regulatory roll-out package
Aitor Azcoaga
Project Team C
6

## Slide 7: Timeline
Deadlines
  2012-12 – Interim report to EC incl. draft CWAs
  2013-06 – 3 months Public consultation & Public conference
  2012-12 – Adoption of CWAs
  2014-02 – Final report to EC incl. approved CWAs
Drafting
WG review
Comments resolution
Public consultation
Comments resolution
Voting
Dec
2013
Aug 2012
Jun
2013
Spring 2013
1
2
3
1
2
4
Project Team input
3
4
Sep
2013

## Slide 8: CEN/WS XBRL planning
Tx | Date |  | Action 1 | Action 2
9 | sep-12 |  | PT kick-off meeting | 
10 | okt-12 |  | Drafting CWAs | 
11 | nov-12 |  | Drafting CWAs | 
12 | dec-12 |  | Interim report to EC | Plenary meeting
13 | jan-13 |  | Drafting CWAs | WS review?
14 | feb-13 |  | Drafting CWAs | WS review?
15 | mrt-13 |  | Drafting CWAs | WS review?
16 | apr-13 |  | Drafting CWAs | Working Group meetings
17 | mei-13 |  | Drafting CWAs | 
18 | jun-13 |  | Public consultation | Public conference meeting
19 | jul-13 |  | Public consultation | 
20 | aug-13 |  | Public consultation | 
21 | sep-13 |  | Comment resolution | 
22 | okt-13 |  | Comment resolution | 
23 | nov-13 |  | Comment resolution | 
24 | dec-13 |  | Plenary meeting + Adoption of CWAs | Satisfaction survey
25 | jan-14 |  | Preperation final report | 
26 | feb-14 |  | Final report to EC | 

## Slide 9: More information
www.eurofiling.info/cen
Chair Ignacio Boixo boixo@eurofiling.info
Secretariat Maarten Peelen Netherlands Standardization institute maarten.peelen@nen.nl